KENYA NATIONAL EXHIBITION PLATFORM
EQUIPMENT, STAFF & SOFTWARE SCHEDULE

Ordered by Procurement Priority • Intel/AMD & Mac Alternatives • Full Staff Plan

# PHASE 0 — IMMEDIATE (Month 1)

Non-negotiable first purchases. No engineering work possible without these.

# 0.1 Workstations — Development Team

| Qty | Role | Primary | Alternative | CPU | RAM | GPU | Storage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Lead Full-Stack Dev | MacBook Pro 16" M4 Max | Dell Precision 7780 | M4 Max 16c / i9-14900HX | 64G / 128G | 40c GPU / RTX 5000 16G | 2TB SSD |
| 2 | Backend/API Dev | Dell Precision 7780 | MacBook Pro 16" M4 Max | i9-14900HX / M4 Max 16c | 128G / 64G | RTX 5000 16G / 40c GPU | 2TB SSD |
| 2 | Frontend/Mobile Dev | MacBook Pro 16" M4 Max | Dell Precision 7780 | M4 Max 16c / i9-14900HX | 64G / 128G | 40c GPU / RTX 5000 16G | 2TB SSD |
| 2 | Security Engineer | Dell Precision 7780 | Lenovo ThinkPad P16 G3 | i9-14900HX | 128G ECC | RTX 5000 Ada 16G | 4TB RAID 1 |
| 2 | 3D Artist (Mobile) | MacBook Pro 16" M4 Max | Dell Precision 7780 | M4 Max 16c / i9-14900HX | 128G | 40c GPU / RTX 5000 16G | 4TB SSD |

Equip 2 of each platform for cross-platform testing. Developer preference assigns primary.

# 0.2 Software Licenses (Annual)

| Qty | Software | Type | Annual (USD) |
| --- | --- | --- | --- |
| 8 | JetBrains All Products Pack | Per-seat | $749/seat |
| 8 | GitHub Enterprise | Per-user/mo | $21/user |
| 8 | Jira / Linear | Per-user/mo | $15/user |
| 4 | Adobe Creative Cloud All Apps | Per-seat | $996/seat |
| 2 | DaVinci Resolve Studio | Perpetual | $295 |
| 10 | CrowdStrike Falcon EDR | Per-endpoint | $250/endpoint |
| 1 | Wazuh SIEM (OSS) | Free | $0 |

# 0.3 Storage & Infrastructure

| Qty | Item | Model | Specs |
| --- | --- | --- | --- |
| 1 | Primary NAS | Synology RS3624RPxs + 12x 24TB RAID 6 | 192TB usable, 10/25GbE, NVMe cache |
| 1 | Backup NAS | Synology RXD1219sas + 12x 24TB | 192TB cold, weekly rotation |
| 2 | Field Backup | QNAP TVS-h874-i9 + 4x 8TB SSD RAID 5 | 24TB portable, 2.5GbE |
| 1 | UPS | APC Smart-UPS 3000VA | NAS + network |

# 0.4 Audio (Field Kit)

| Qty | Item | Model | Specs |
| --- | --- | --- | --- |
| 2 | Ambisonic Mic | Sennheiser AMBEO VR Mic | 4 capsules, binaural monitoring |
| 2 | Field Recorder | Sound Devices MixPre-10 II | 10 inputs, 32-bit float, timecode |
| 1 | Binaural Mic | 3Dio Free Space Pro II + KE-213 | Human-ear form, omni capsules |
| 2 | Boom Mic | Sennheiser MKH 416 | Short shotgun, RF condenser |
| 2 | Wireless Lav | DJI Mic 2 (2TX+1RX) | 250m range, internal recording |
| 2 | Boom Pole | K-Tek Aura Plus 3-6m | Carbon fibre, internal cable |
| 1 | Wind Protection | RyCote Blimp + fur | Full wind isolation |

# PHASE 1 — PILOT PRODUCTION (Months 2-3)

Capture gear for pilot county content. Creative team starts.

# 1.1 Camera & Video

| Qty | Item | Exact Model | Specs |
| --- | --- | --- | --- |
| 2 | Cinema Drone | DJI Inspire 3 + Zenmuse X9-8K | 8K FF, ProRes RAW, 14+ stops, 15km O3 |
| 3 | 360° Camera | Insta360 Pro 2 | 8K 30fps 3D 360°, 6-lens, HDR |
| 2 | 360° Backup | Insta360 X4 | 8K 30fps, waterproof 10m |
| 1 | Cinema Camera | RED V-RAPTOR XL 8K VV (alt: Sony VENICE 2) | 8K FF, 17+ stops, 8K 120fps |
| 5 | Cinema Lenses | Canon CN-E 24/35/50/85mm T1.5 + 24-70 T2.9 | FF primes + zoom, EF mount |
| 2 | Photogrammetry Camera | Sony A7R V + FE 24-70 f/2.8 GM II | 61MP, GPS tagging, intervalometer |
| 1 | LIDAR Scanner | Leica BLK360 (alt: FARO S350) | 360°, 2mm@20m accuracy |
| 4 | Action Cam | GoPro HERO13 (2x) + DJI Action 5 Pro (2x) | 5.3K 60fps, waterproof |
| 1 | Gimbal | DJI RS 4 Pro | 3-axis, 10kg payload |
| 1 | Tripod | Sachtler FSB 14 + ENG carbon | 14kg payload |
| 1 | Field Monitor | SmallHD Cine 13" UltraBright | 1300 nits, outdoor |
| 2 | ND Filter Kit | 4x5.65" Tiffen ND 0.3-2.4 | Bright outdoor shooting |

# 1.2 Render & Infrastructure

| Qty | Item | Model | Specs |
| --- | --- | --- | --- |
| 2 | Render Node | Custom: 4x RTX 6000 Ada, AMD EPYC 9654, 512GB | 4x RTX 6000 Ada per node. Expandable to 8x. |
| 1 | Network Switch | Mellanox ConnectX-7 200GbE InfiniBand | GPU interconnect |
| 1 | UPS x4 | APC Smart-UPS 1500 | Per render node |
| 2 | Field Internet | Starlink Mini | Portable satellite, 50-100Mbps |
| 2 | Field Router | Huawei 5G CPE Pro 2 | 5G NR, Wi-Fi 6 |
| 2 | Mobile Hotspot | GlocalMe G4 Pro | Global eSIM, 4G/5G |

# 1.3 Staff — Content Production (Month 2-3)

| Role | Key Skills |
| --- | --- |
| Senior 3D Artist / Tech Artist | Unreal 5.5, Maya, Houdini, photogrammetry, PBR |
| Junior 3D Artist | Maya/Blender, Substance, Unity, texture baking |
| Drone Pilot / Aerial Camera Op | KCAA license, DJI Inspire 3, aerial 8K/360° |
| Field Camera Operator | RED/Sony, 360° rigs, lighting, field audio |
| Audio Engineer / Sound Designer | Pro Tools, ambisonic, field recording, iZotope |
| Video Editor / Colourist | DaVinci Resolve, Premiere, 360° editing |
| Technical Writer | API/docs, technical writing, diagrams |
| Technical Support Engineer | Laravel support, bug triage, monitoring |

# PHASE 2 — KICC FLAGSHIP BOOTH (Months 4-9)

Physical 4D experience zones at KICC. 3 zones initial installation.

# 2.1 Content Creation Workstations

| Qty | Role | Primary | Alternative | CPU | RAM | GPU | Storage | Display |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Sr 3D Artist | Custom Workstation | Custom (Intel) | Threadripper PRO 7995WX / Xeon w9-3495X | 256GB ECC | 2x RTX 6000 Ada 96GB | 8TB NVMe RAID 0 | Dell UP3218K 8K + BenQ PD3220U 4K |
| 1 | Jr 3D Artist | Custom Workstation | Custom (Intel) | Threadripper PRO 7975WX / i9-14900K | 128GB ECC | RTX 6000 Ada 48GB | 4TB NVMe | BenQ PD3220U 4K |

# 2.2 3D Software Licenses

| Qty | Software | Type | Annual (USD) |
| --- | --- | --- | --- |
| 4 | Unreal Engine 5.5 Enterprise | Per-seat | $1,500/seat |
| 2 | Unity 6 Industrial | Per-seat | $4,500/seat |
| 1 | Cesium ion Platform | Usage | $12,000/yr |
| 3 | Autodesk Maya | Per-seat | $1,875/seat |
| 2 | ZBrush | Perpetual | $995 + $45/yr |
| 2 | Substance 3D Designer+Painter | Enterprise | $1,200/seat |
| 2 | Houdini FX | Per-seat | $4,495/seat |
| 1 | RealityCapture | Perpetual | $6,500 |
| 2 | iZotope RX Advanced | Perpetual | $1,199 |
| 2 | Avid Pro Tools Studio | Per-seat | $299/seat |
| 1 | Dolby Atmos Production Suite | Perpetual | $299 |

# 2.3 Booth Hardware (per flagship zone)

| Qty | Item | Exact Model | Specs |
| --- | --- | --- | --- |
| 2-3 | Projector | Barco UDX-4K40 | 40K lumens, 4K, laser, 30K hr, 3-chip DLP |
| 1 | Curved Screen | Custom 270° rigid (Screen Excellence) | Seamless, acoustic-transparent |
| 1 | Dome Screen | Custom 360° + perforated (Fulldome.pro) | Ventilated, acoustic-transparent |
| 1 | Motion Platform | D-BOX 6-DOF | 6-DOF, 5000kg, haptic API |
| 1 | Scent System | Olorama Scent Pack 8ch | HVAC-integrated, DMX, 0.1s |
| 1 | HVAC Zone | Mitsubishi VRF + spot heaters | BACnet, precision zoning |
| 1 | Wind System | Custom DMX fan array | Variable-speed, multi-unit |
| 19+ | Spatial Audio | L-Acoustics L-ISA | Object-based 3D, 19+ speakers |
| 1 | Lighting Console | ETC Eos Apex 10 | Full DMX show control |
| 1 set | Lighting | ETC Source 4 LED S3 + Chauvet COLORado | Key + ambient + pixel LED |
| 1 | Haze Machine | MDG theONE | Ultra-fine, silent, 10-min suspension |
| 1-2 | Touch Table | Ideum Pro 65" 4K / 55" 4K | 60-point multi-touch, i9+RTX 3060 |
| 20 | VR Headset | Meta Quest 3 512GB | Standalone, colour passthrough |
| 2 | VR Headset (VIP) | Apple Vision Pro | Micro-OLED 23M pixels |
| 2 | VR Headset (Dev) | Valve Index full kit | 144Hz, finger tracking |
| 12 | Mobile Device Lab | Samsung S24U, Pixel 8 Pro, iPhone 16 Pro, Infinix Zero 40, Tecno Phantom V Fold, Nokia G42 x2 | Flagship + Kenyan market coverage |

# 2.4 Staff — Booth Build (Month 4-9)

| Role | Qty | Monthly (KES) | Skills |
| --- | --- | --- | --- |
| AV / Booth Engineer | 2 | 300,000 | Barco, D-BOX, L-Acoustics, ETC, DMX |
| Systems Integrator | 1 | 350,000 | Q-SYS/Medialon, Unreal, show control |

TOTAL Phase 2 Staff: 36 people | KES 7,860,000/month

Phase 2 Total: ~$1,600,000 (equipment + software) + KES 7.86M (staff/month)

# PHASE 3 — COUNTY HUBS (Months 9-15)

Scaled-down pods for 5-10 county locations.

# 3.1 Hub Hardware (per county pod)

| Qty | Item | Model | Specs |
| --- | --- | --- | --- |
| 1-2 | Projector | Sony VPL-FHZ131 | 13K lumens, WUXGA, laser |
| 1 | Screen | ReAct 3.1 curved tension | Ambient light rejecting |
| 1 | Motion Platform | E2Motion EM-2000 2-DOF | 2-DOF, 2000kg |
| 1 set | Spatial Audio | Genelec 8030C 7.1.4 Atmos | 7+1+4, studio monitors |
| 1 | Touch Table | Ideum Pro 55" 4K | 60-point multi-touch, i9+RTX 3060 |
| 6 | VR Headset | Meta Quest 3 512GB | Standalone VR |

# 3.2 Additional Servers

| Qty | Item | Model | Specs |
| --- | --- | --- | --- |
| 2 | Render Node | 4x RTX 6000 Ada, EPYC 9654, 512GB | Add to existing Phase 1 cluster |

# 3.3 Staff — Hub Operations (Month 9-15)

| Role | Qty | Monthly (KES) | Skills |
| --- | --- | --- | --- |
| County Hub Technician | 5 | 150,000 | AV maintenance, IT support, VR headset mgmt |

TOTAL Phase 3 Staff: 41 people | KES 8,610,000/month

Phase 3 Total: ~$170,000/hub + KES 8.61M (staff/month)

# PHASE 4 — SCALE (Month 15+)

| Qty | Item | Model | Specs |
| --- | --- | --- | --- |
| 2 | Addl Field Teams | Full camera + audio + laptop kit | Duplicate Phase 0+1 gear |
| 2 | Addl Render Nodes | 8x RTX 6000 Ada, EPYC 9654, 1TB | Double render capacity |
| 1 | NAS Expansion | Synology expansion + 12x 24TB | Scale media library |
| 2 | Addl Connectivity | Starlink Mini + Huawei 5G CPE Pro 2 | Multi-team field support |
| - | Annual Refresh | 10% of equipment value | Batteries, cards, laptop cycles |

# 4.1 Staff Expansion (Phase 4+)

| Role | Qty | Monthly (KES) | Notes |
| --- | --- | --- | --- |
| Additional Field Teams | +10 | +KES 2M | Scale with county coverage expansion |

Phase 4 Total: ~$350,000 + scaling staff costs

# BUDGET SUMMARY

| Phase | Equipment | Staff/mo | Duration | Total USD | Total KES |
| --- | --- | --- | --- | --- | --- |
| 0 — Immediate | $225,000 | KES 4.96M | Month 1 | $225,000 | KES 29.3M |
| 1 — Pilot | $480,000 | KES 7.21M | Months 2-3 | $480,000 | KES 62.4M |
| 2 — KICC Booth | $1,600,000 | KES 7.86M | Months 4-9 | $1,600,000 | KES 208M |
| 3 — Hubs (10) | $1,700,000 | KES 8.61M | Months 9-15 | $1,700,000 | KES 221M |
| 4 — Scale | $350,000 | Variable | Month 16+ | $350,000 | KES 45.5M |
| TOTAL EQUIPMENT |  |  |  | $4,355,000 | KES 566.2M |

# TOTAL PROJECT INVESTMENT (18 MONTHS)

| Category | USD | KES |
| --- | --- | --- |
| Equipment & Software | $4,355,000 | KES 566,200,000 |
| Staff (18 months, all phases) | $1,800,000 | KES 234,000,000 |
| GRAND TOTAL | $6,155,000 | KES 800,200,000 |

# RECRUITMENT NOTES

Month 1: Hire Tech Lead, Full-Stack Engineers, Platform Admin — they build the foundation.

Month 1: QA Engineer and Tech Writer start immediately — test infra and docs are built alongside code, not retrofitted.

Month 2-3: Content team starts (3D artists, drone, camera, audio) — gear arrives, production begins.

Month 4: Booth engineers hired — after pilot content captured and KICC design finalized.

Month 9+: County Hub Technicians hired — after hardware procured and installed.

Contract specialist roles (drone pilots, audio engineers, hub techs) where possible to reduce fixed overhead.

All staff based in Nairobi with regular county travel for field teams.