KENYA NATIONAL EXHIBITION PLATFORM

PROJECT EQUIPMENT, STAFF & PROCUREMENT CATALOGUE

Complete reference for the Team Leader
All specifications • All roles • Phased by priority

Version 2.0 — July 2026
Prepared for KICC Engineering, Nairobi

# How to Use This Catalogue

This document is structured in procurement phases. Each phase groups the equipment, software, and staff you need to acquire or hire at that stage. You cannot skip phases — Phase 0 items are prerequisites for Phase 1, and so on.

Every workstation comes with a primary and an alternative model (Intel/AMD where available) so you are never locked into a single vendor. Order the primary first; use the alternative if stock or budget requires.

Staff roles list the exact skills required. Use these as the job description basis when advertising.

# Contents

Phase 0 — Immediate (Month 1)

0.1 Workstations — Development & Engineering Team

0.2 Software & Services Licenses

0.3 Storage & Network Infrastructure

0.4 Audio Field Kit

0.5 Staff to Hire — Engineering & Administration

Phase 1 — Pilot Production (Months 2-3)

1.1 Camera & Video Equipment

1.2 Render Farm & Field Connectivity

1.3 Staff to Hire — Content Production & Support

Phase 2 — KICC Flagship Booth (Months 4-9)

2.1 3D Content Creation Workstations

2.2 3D & VFX Software Licenses

2.3 Booth Hardware (per flagship experience zone)

2.4 Staff to Hire — Booth Engineering

Phase 3 — County Hubs (Months 9-15)

3.1 Hub Hardware (per county pod)

3.2 Staff to Hire — Hub Operations

Phase 4 — Scale & Expansion (Month 15+)

Budget Summary

Total Project Investment (18 Months)

Recruitment Timeline & Notes

# PHASE 0 — IMMEDIATE (Month 1)

These are the non-negotiable first purchases. Nothing else can start until the engineering team has workstations, storage, and software. Place orders on Day 1.

## 0.1 Workstations — Development & Engineering Team

Every role lists a primary model and an alternative. Order primary if available. Use alternative only if primary has stock or budget issues.

| Qty | Role | Primary Model | Alternative (Intel/AMD) | CPU | RAM | GPU | Storage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Lead Full-Stack Developer | MacBook Pro 16" M4 Max | Dell Precision 7780 | M4 Max 16-core / Intel i9-14900HX | 64GB / 128GB | 40-core GPU / RTX 5000 Ada 16GB | 2TB SSD |
| 2 | Backend / API Developer | Dell Precision 7780 | MacBook Pro 16" M4 Max | Intel i9-14900HX / M4 Max 16-core | 128GB / 64GB | RTX 5000 Ada 16GB / 40-core GPU | 2TB SSD |
| 2 | Frontend / Mobile Developer | MacBook Pro 16" M4 Max | Dell Precision 7780 | M4 Max 16-core / Intel i9-14900HX | 64GB / 128GB | 40-core GPU / RTX 5000 Ada 16GB | 2TB SSD |
| 2 | Security Engineer | Dell Precision 7780 | Lenovo ThinkPad P16 Gen 3 | Intel i9-14900HX | 128GB DDR5 ECC | RTX 5000 Ada 16GB | 4TB NVMe RAID 1 |
| 2 | 3D Artist (Mobile/Field) | MacBook Pro 16" M4 Max | Dell Precision 7780 | M4 Max 16-core / Intel i9-14900HX | 128GB Unified / 128GB | 40-core GPU / RTX 5000 Ada 16GB | 4TB SSD |

Note: Equip 2 of each platform to ensure cross-platform testing. Developer preference assigns primary.

## 0.2 Software & Services Licenses

| Qty | Software | License Model | Annual Cost (USD) |
| --- | --- | --- | --- |
| 8 | JetBrains All Products Pack (incl. DataGrip) | Per-seat subscription | $749/seat |
| 8 | GitHub Enterprise | Per-user / month | $21/user |
| 8 | Jira / Linear (project management) | Per-user / month | $15/user |
| 4 | Adobe Creative Cloud All Apps | Per-seat annual | $996/seat |
| 2 | DaVinci Resolve Studio (colour grading) | Perpetual license | $295 (one-time) |
| 10 | CrowdStrike Falcon (endpoint security) | Per-endpoint / year | $250/endpoint |
| 1 | Wazuh SIEM (security monitoring) | Open-source (free) | $0 |

## 0.3 Storage & Network Infrastructure

| Qty | Item | Model | Specification |
| --- | --- | --- | --- |
| 1 | Primary NAS | Synology RS3624RPxs + 12x 24TB Seagate Exos HDD (RAID 6) | 192TB usable, NVMe read cache, 10GbE + 25GbE, redundant PSU |
| 1 | Backup NAS | Synology RXD1219sas expansion + 12x 24TB Exos | 192TB cold backup, rotated weekly off-site |
| 2 | Field Backup Server | QNAP TVS-h874-i9 + 4x 8TB Samsung 870 EVO (RAID 5) | 24TB portable SSD, 2.5GbE, compact for field deployment |
| 1 | UPS (NAS & Network) | APC Smart-UPS 3000VA | Protects all studio infrastructure |

## 0.4 Audio Field Kit

Complete field audio capture kit for a 2-person sound team. Buy one kit; duplicate in Phase 4 for a second team.

| Qty | Item | Model | Specification |
| --- | --- | --- | --- |
| 2 | Ambisonic Microphone | Sennheiser AMBEO VR Mic | First-order ambisonic, 4 matched capsules, binaural monitoring output |
| 2 | Field Recorder | Sound Devices MixPre-10 II | 10 inputs, 32-bit float recording, timecode I/O, dual SD slots |
| 1 | Binaural Microphone | 3Dio Free Space Pro II + Sennheiser KE-213 capsules | Human-ear form factor, omni capsules, for headphone-based 3D audio |
| 2 | Boom Microphone | Sennheiser MKH 416 | Short shotgun, RF condenser, excellent off-axis rejection |
| 2 | Wireless Lavalier | DJI Mic 2 (2 transmitters + 1 receiver per kit) | 250m range, internal recording backup, compact clip-on |
| 2 | Boom Pole | K-Tek Aura Plus (3-6m) | Carbon fibre, internal cable routing, internal dampening |
| 1 | Wind Protection Kit | RyCote Blimp + full fur windscreen | Complete wind isolation for outdoor boom operation |

## 0.5 Staff to Hire — Engineering & Administration

These 20 people must start in Month 1. They build the platform foundation.

| Role | Qty | Monthly (KES) | Key Qualifications Required |
| --- | --- | --- | --- |
| Full-Stack Software Engineer (Laravel/PHP) | 4 | 250,000 | Laravel 11, PHP 8.2+, MySQL, REST API design, Redis, Bootstrap 5, JavaScript, HTML5/CSS3 |
| Python / ML Engineer | 2 | 300,000 | Python 3.12+, PyTorch/scikit-learn, NLP, vector embeddings, API development |
| Frontend Developer (React/Next.js) | 2 | 220,000 | React 19, Next.js 15, TypeScript, Tailwind/Bootstrap, responsive design |
| Mobile Developer (Unity/C#) | 2 | 280,000 | Unity 6, C#, iOS/Android build pipeline, 3D rendering optimisation, AR/VR |
| Cybersecurity Engineer | 2 | 350,000 | Penetration testing (Burp, Metasploit), SIEM (Wazuh), OWASP Top 10, NIS coordination |
| Database Administrator | 1 | 250,000 | MySQL 8.4, MariaDB, query optimisation, replication, backup/DR, Percona Toolkit |
| DevOps Engineer | 1 | 280,000 | Linux (Ubuntu), Nginx, Docker, CI/CD (GitHub Actions), Prometheus/Grafana |
| Technical Lead / Architect | 1 | 450,000 | Full-stack architecture, Laravel/Python, team leadership, technical roadmap |
| Product Manager | 1 | 300,000 | Product strategy, stakeholder management, sprint planning, county liaison |
| QA Engineer | 1 | 200,000 | PHPUnit, Laravel Dusk, k6, manual + automated testing, regression suites |
| Platform Administrator | 2 | 150,000 | Content moderation, vendor verification, user management, support ticketing |
| Content Manager / Coordinator | 1 | 180,000 | Production scheduling, county liaison, quality control, pipeline management |

Subtotal: 20 people • KES 4,960,000 per month

Phase 0 Estimated Cost: USD 225,000 (equipment) + KES 4.96M/month (staff)

# PHASE 1 — PILOT PRODUCTION (Months 2-3)

Capture equipment for pilot county content. Order these while Phase 0 staff are building the software platform. Content team hires start here.

## 1.1 Camera & Video Equipment

| Qty | Item | Model | Specification |
| --- | --- | --- | --- |
| 2 | Cinema Drone | DJI Inspire 3 + Zenmuse X9-8K gimbal | 8K full-frame sensor, ProRes RAW, 14+ stops dynamic range, O3 Pro 15km transmission |
| 3 | 360° Camera (Primary) | Insta360 Pro 2 | 8K 30fps 3D 360°, 6-lens design, FlowState stabilisation, HDR mode |
| 2 | 360° Camera (Backup) | Insta360 X4 | 8K 30fps 360°, waterproof to 10m, compact for quick captures |
| 1 | Cinema Camera | RED V-RAPTOR XL 8K VV | 8K full-frame, 17+ stops dynamic range, 8K at 120fps, REDCODE RAW and ProRes |
| 1 | Alternative Cinema Camera | Sony VENICE 2 (8K) | Use if RED availability or support is a concern. Dual ISO 800/3200. |
| 5 | Cinema Lenses | Canon CN-E 24/35/50/85mm T1.5 + 24-70mm T2.9 zoom | Full-frame cinema primes + zoom, EF mount, for RED V-RAPTOR |
| 2 | Photogrammetry Camera | Sony A7R V + FE 24-70mm f/2.8 GM II | 61MP full-frame, GPS tagging, built-in intervalometer for automated capture |
| 1 | LIDAR Scanner | Leica BLK360 (alternative: FARO Focus S350) | 360° scanning, 2mm accuracy at 20m, HDR spherical image overlay |
| 4 | Action Camera | GoPro HERO13 Black (2x) + DJI Osmo Action 5 Pro (2x) | 5.3K 60fps, waterproof, GPS sticker telemetry, various mounts |
| 1 | Camera Gimbal | DJI RS 4 Pro | 3-axis stabilisation, 10kg payload, dual-grip handle |
| 1 | Tripod | Sachtler FSB 14 with ENG carbon-fibre tripod | 14kg payload, 75mm ball base, carbon-fibre legs |
| 1 | Field Monitor | SmallHD Cine 13" UltraBright | 1300 nits brightness, outdoor-viewable, false-colour and waveform |
| 2 | ND Filter Kit | 4x5.65" Tiffen ND set (0.3 to 2.4) | Essential for controlling exposure in bright outdoor conditions |

## 1.2 Render Farm & Field Connectivity

| Qty | Item | Model | Specification |
| --- | --- | --- | --- |
| 2 | Render Node | Custom: 4x NVIDIA RTX 6000 Ada, AMD EPYC 9654, 512GB DDR5 ECC | GPU rendering (V-Ray, Redshift, Octane). Expandable to 8x GPUs per node later. |
| 1 | Render Network Switch | Mellanox ConnectX-7 200GbE InfiniBand | High-speed GPU-to-GPU communication for distributed rendering |
| 4 | UPS for Render Nodes | APC Smart-UPS 1500 (one per node) | Clean power delivery and graceful shutdown on power loss |
| 2 | Field Internet Terminal | Starlink Mini | Portable satellite internet, 50-100 Mbps, low-latency, battery-powered |
| 2 | Field 5G Router | Huawei 5G CPE Pro 2 | 5G NR, Wi-Fi 6, carrier aggregation for multiple SIMs |
| 2 | Global Mobile Hotspot | GlocalMe G4 Pro | Global eSIM, 4G/5G, multi-carrier failover for inter-county travel |

## 1.3 Staff to Hire — Content Production & Support

These 13 people start in Month 2. Recruit during Month 1.

| Role | Qty | Monthly (KES) | Key Qualifications Required |
| --- | --- | --- | --- |
| Senior 3D Artist / Technical Artist | 2 | 350,000 | Unreal Engine 5.5, Maya, Houdini, photogrammetry pipeline, PBR texturing, LOD optimisation |
| Junior 3D Artist | 2 | 180,000 | Maya/Blender, Substance Painter, Unity, texture baking, asset library management |
| Drone Pilot / Aerial Camera Operator | 2 | 200,000 | KCAA Remote Pilot Licence, DJI Inspire 3 operation, aerial cinematography |
| Field Camera Operator | 2 | 180,000 | RED/Sony cinema camera operation, 360° rigs, lighting setup, field audio basics |
| Audio Engineer / Sound Designer | 1 | 250,000 | Pro Tools, ambisonic/spatial audio mixing, field recording, iZotope RX restoration |
| Video Editor / Colourist | 1 | 200,000 | DaVinci Resolve Studio, Premiere Pro, 360° video editing, colour grading |
| Technical Writer | 1 | 180,000 | API documentation, technical writing, diagram creation, document management |
| Technical Support Engineer | 2 | 180,000 | Laravel application support, bug reproduction/triage, on-call incident response |

Subtotal: 33 people total • KES 7,210,000 per month

Phase 1 Estimated Cost: USD 480,000 (equipment) + KES 7.21M/month (staff)

# PHASE 2 — KICC FLAGSHIP BOOTH (Months 4-9)

Build-out of the physical 4D experience zones at KICC. Initial installation: 3 experience zones.

## 2.1 3D Content Creation Workstations

| Qty | Role | Primary | Alternative | CPU | RAM | GPU | Storage | Display |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Senior 3D Artist | Custom Workstation | Custom (Intel) | AMD Threadripper PRO 7995WX 96-core / Intel Xeon w9-3495X | 256GB DDR5 ECC | 2x NVIDIA RTX 6000 Ada (96GB total) | 8TB NVMe RAID 0 | Dell UP3218K 32" 8K + BenQ PD3220U 32" 4K reference |
| 1 | Junior 3D Artist | Custom Workstation | Custom (Intel) | AMD Threadripper PRO 7975WX / Intel Core i9-14900K | 128GB DDR5 ECC | 1x NVIDIA RTX 6000 Ada (48GB) | 4TB NVMe | BenQ PD3220U 32" 4K |

## 2.2 3D & VFX Software Licenses

| Qty | Software | License Model | Annual Cost (USD) |
| --- | --- | --- | --- |
| 4 | Unreal Engine 5.5 Enterprise | Per-seat enterprise license | $1,500/seat |
| 2 | Unity 6 Industrial | Per-seat annual | $4,500/seat |
| 1 | Cesium ion Platform | Usage-based subscription | $12,000/year |
| 3 | Autodesk Maya | Per-seat annual | $1,875/seat |
| 2 | ZBrush | Perpetual + annual upgrade | $995 + $45/year |
| 2 | Substance 3D Designer + Painter | Per-seat Enterprise annual | $1,200/seat |
| 2 | Houdini FX | Per-seat annual | $4,495/seat |
| 1 | RealityCapture | Perpetual commercial license | $6,500 (one-time) |
| 2 | iZotope RX Advanced | Perpetual license | $1,199 (one-time) |
| 2 | Avid Pro Tools Studio | Per-seat annual | $299/seat |
| 1 | Dolby Atmos Production Suite | Perpetual license | $299 (one-time) |

## 2.3 Booth Hardware (per flagship experience zone)

Each KICC zone requires the following. Multiply quantities by number of zones (recommended 3 for launch).

| Qty | Item | Model | Specification |
| --- | --- | --- | --- |
| 2-3 | Laser Projector | Barco UDX-4K40 | 40,000 lumens, 4K UHD resolution, laser phosphor light source, 30,000-hour lifespan, 3-chip DLP |
| 1 | Curved Screen | Custom 270° rigid (Screen Excellence) | Seamless curved surface, acoustic-transparent for behind-screen speakers |
| 1 | Dome Screen | Custom 360° dome + perforated screen (Fulldome.pro) | Full dome, perforated for acoustic transparency and ventilation |
| 1 | Motion Platform | D-BOX 6-DOF Motion Platform | 6 degrees of freedom (heave, surge, sway, pitch, roll, yaw), 5,000kg payload |
| 1 | Scent System | Olorama Scent Pack (8+ channels) | HVAC-integrated atomisation, DMX-controlled, 0.1-second response, medical-grade oils |
| 1 | HVAC Zone | Mitsubishi Heavy Industries VRF + spot heaters/coolers | Precision temperature zoning, BACnet integration with show control |
| 1 | Wind System | Custom DMX-controlled fan array | Multiple variable-speed directional fans, gust simulation, DMX addressable |
| 19+ | Spatial Audio | L-Acoustics L-ISA immersive sound system | 19+ speakers, object-based audio mixing, precise 3D sound localisation |
| 7.1.4 | Spatial Audio (Hub alternative) | Genelec 8030C Dolby Atmos configuration | 7 ear-level + 1 subwoofer + 4 ceiling monitors, for county hub installations |
| 1 | Lighting Console | ETC Eos Apex 10 | Full DMX show control, integrated with motion and audio timeline |
| 1 set | Lighting Fixtures | ETC Source 4 LED Series 3 + Chauvet COLORado 72 IP | Key lighting follow-spots, ambient colour wash, pixel LED strip effects |
| 1 | Haze Machine | MDG theONE (or Look Solutions Unique 2) | Ultra-fine vapour, silent operation, 10-minute atmospheric suspension |
| 1-2 | Touch-Interactive Table | Ideum Pro 65" 4K (flagship) / 55" 4K (hub) | 60-point multi-touch, 4K display, built-in PC (Intel i9, NVIDIA RTX 3060), Gorilla Glass |
| 20 | VR Headset (Venue) | Meta Quest 3 — 512GB | Standalone VR, colour passthrough AR, hand tracking, no PC required |
| 2 | VR Headset (VIP experience) | Apple Vision Pro | Micro-OLED 23 million pixels, premium VIP content review |
| 2 | VR Headset (Development) | Valve Index Full Kit | 144Hz refresh, 2160x1600 per eye, finger-tracking controllers |
| 12 | Mobile Device Lab | Samsung S24 Ultra, Pixel 8 Pro, iPhone 16 Pro Max, Infinix Zero 40, Tecno Phantom V Fold, Nokia G42 (2x each) | Covers flagship + Kenyan market budget phones for testing |

## 2.4 Staff to Hire — Booth Engineering

| Role | Qty | Monthly (KES) | Key Qualifications Required |
| --- | --- | --- | --- |
| AV / Booth Engineer | 2 | 300,000 | Barco projection, D-BOX motion platforms, L-Acoustics audio, ETC lighting, DMX show control programming |
| Systems Integrator | 1 | 350,000 | Hardware-software integration, Q-SYS/Medialon show control, Unreal Engine timeline plugins |

Subtotal: 36 people total • KES 7,860,000 per month

Phase 2 Estimated Cost: USD 1,600,000 (equipment + software) + KES 7.86M/month (staff)

# PHASE 3 — COUNTY HUBS (Months 9-15)

Scaled-down immersive pods for 5 to 10 county locations. Each hub costs approximately USD 170,000.

## 3.1 Hub Hardware (per county pod)

| Qty | Item | Model | Specification |
| --- | --- | --- | --- |
| 1-2 | Projector | Sony VPL-FHZ131 | 13,000 lumens, WUXGA resolution, laser light source, compact form factor |
| 1 | Projection Screen | ReAct 3.1 curved tension screen | Ambient-light-rejecting surface, tensioned for wrinkle-free flatness |
| 1 | Motion Platform | E2Motion EM-2000 2-DOF | 2 degrees of freedom (heave + pitch), 2,000kg payload, single-person |
| 1 set | Spatial Audio | Genelec 8030C 7.1.4 Dolby Atmos | 7 ear-level + 1 subwoofer + 4 ceiling-mounted studio monitors |
| 1 | Touch Table | Ideum Pro 55" 4K | 60-point multi-touch, 4K, built-in i9 + RTX 3060, Gorilla Glass |
| 6 | VR Headset | Meta Quest 3 512GB | Standalone VR for hub visitors |

## 3.2 Additional Render Capacity

| Qty | Item | Model | Specs |
| --- | --- | --- | --- |
| 2 | Render Node | Custom: 4x RTX 6000 Ada, AMD EPYC 9654, 512GB | Add to existing Phase 1 cluster for hub content processing |

## 3.3 Staff to Hire — Hub Operations

| Role | Qty | Monthly (KES) | Key Qualifications Required |
| --- | --- | --- | --- |
| County Hub Technician | 5 | 150,000 | AV equipment maintenance, basic IT support, Unity touch table operations, VR headset management |

Subtotal: 41 people total • KES 8,610,000 per month

Phase 3 Estimated Cost: USD 170,000 per hub + KES 8.61M/month (staff)

# PHASE 4 — SCALE & EXPANSION (Month 15+)

Duplicate capacity as county coverage expands beyond the initial hubs.

| Qty | Item | Model | Specification |
| --- | --- | --- | --- |
| 2 | Additional Field Production Teams | Full gear kit (duplicate Phase 0 workstations + Phase 1 camera/audio) | Enables parallel capture across multiple counties simultaneously |
| 2 | Additional Render Nodes | Custom: 8x RTX 6000 Ada, AMD EPYC 9654, 1TB | Double existing render capacity for increased content pipeline |
| 1 | NAS Expansion Unit | Synology expansion chassis + 12x 24TB HDD | Scale media library storage for growing asset count |
| 2 | Additional Field Connectivity | Starlink Mini + Huawei 5G CPE Pro 2 | Support multiple field teams operating simultaneously |
| - | Annual Equipment Refresh | 10% of total equipment value per year | Media cards, batteries, laptop replacement cycles, consumables |

Phase 4 Estimated Cost: USD 350,000 + scaling staff costs

# BUDGET SUMMARY

| Phase | Equipment & Software | Staff/month | Duration | Total USD | Total KES |
| --- | --- | --- | --- | --- | --- |
| 0 — Immediate | $225,000 | KES 4.96M | Month 1 | $225,000 | KES 29.3M |
| 1 — Pilot | $480,000 | KES 7.21M | Months 2-3 | $480,000 | KES 62.4M |
| 2 — KICC Booth (3 zones) | $1,600,000 | KES 7.86M | Months 4-9 | $1,600,000 | KES 208M |
| 3 — County Hubs (10 pods) | $1,700,000 | KES 8.61M | Months 9-15 | $1,700,000 | KES 221M |
| 4 — Scale & Expansion | $350,000 | Variable | Month 16+ | $350,000 | KES 45.5M |
| EQUIPMENT TOTAL |  |  |  | $4,355,000 | KES 566.2M |

# TOTAL PROJECT INVESTMENT (18 Months)

| Category | USD | KES (at 130) |
| --- | --- | --- |
| Equipment & Software (all phases) | $4,355,000 | KES 566,200,000 |
| Staff (all phases, 18 months) | $1,800,000 | KES 234,000,000 |
| GRAND TOTAL | $6,155,000 | KES 800,200,000 |

# RECRUITMENT TIMELINE

| Timeline | Hire | Headcount |
| --- | --- | --- |
| Month 1 | Tech Lead, 4x Full-Stack, 2x ML, 2x Frontend, 2x Mobile, 2x Security, DBA, DevOps, PM, QA, 2x Platform Admin, Content Coordinator | 20 |
| Month 2-3 | 2x Sr 3D Artist, 2x Jr 3D Artist, 2x Drone Pilot, 2x Camera Op, Audio Eng, Video Editor, Tech Writer, 2x Tech Support | +13 = 33 |
| Month 4-9 | 2x AV/Booth Engineer, Systems Integrator | +3 = 36 |
| Month 9-15 | 5x County Hub Technician | +5 = 41 |
| Month 16+ | Additional field teams + specialists | +10 = 51+ |

# KEY NOTES FOR THE TEAM LEADER

- Order Phase 0 items on Day 1. Workstations have 2-4 week lead times. Delays here delay everything.

- DRONE PILOT: Must hold a valid KCAA Remote Pilot Licence. Include this in the job advertisement.

- CAMERA: RED V-RAPTOR can be substituted with Sony VENICE 2 if RED availability is a concern. Both deliver 8K cinema quality.

- BOOTH HARDWARE: Obtain quotes from D-BOX, L-Acoustics, and Barco directly. Prices vary significantly with configuration.

- SOFTWARE: Autodesk, Adobe, and Avid offer education/government discounts. Request these before purchasing at retail.

- STAFF: Contract drone pilots, audio engineers, and hub technicians rather than hiring permanently. Reduces fixed overhead.

- CONTINGENCY: Budget 15% above listed prices for shipping, taxes, import duties, and price changes between quotation and purchase.