PHASE 0 — IMMEDIATE PROCUREMENT & HIRING

Detailed Expansion for the Team Leader
Everything to order and hire in Month 1

KICC National Exhibition Platform • July 2026

# Phase 0 Overview

Phase 0 covers everything you must order and hire in the first month. Nothing in Phase 1 can begin until these items arrive and these staff are onboarded.

Estimated total: USD 225,000 (equipment) + KES 4,960,000 (first month staff cost).

Lead times are noted for every item. Items with 4+ week lead times should be ordered on Day 1.

# What Arrives in Phase 0

| Deliverable | Items Included | Lead Time | When Ready |
| --- | --- | --- | --- |
| Workstations (10 units) | 4x MacBook Pro M4 Max, 4x Dell Precision 7780, 2x MacBook Pro 14" M4 Pro | 2-4 weeks | Week 3-4 |
| Software Licenses | JetBrains, GitHub, Jira, Adobe, DaVinci, CrowdStrike, Wazuh | Instant (download) | Day 1-3 |
| Storage Infrastructure | Synology NAS (192TB), Synology backup (192TB), QNAP field servers (2x 24TB), UPS | 1-3 weeks | Week 2-4 |
| Audio Field Kit | AMBEO mic, MixPre-10, 3Dio, MKH 416, DJI Mic 2, K-Tek poles, RyCote blimp | 1-3 weeks | Week 3-4 |
| Staff Onboarded | 20 engineers, admins, and coordinators | Recruitment in Month 0 | Week 1-4 |

# 1. Workstations — Detailed Specifications

# 1.1 Lead Full-Stack Developer (x2)

Builds the platform backend and API. Primary desktop environment for 8+ hours daily.

| Spec | Primary (Mac) | Alternative (Intel/AMD) |
| --- | --- | --- |
| Model | Apple MacBook Pro 16" M4 Max | Dell Precision 7780 Workstation |
| Supplier | Apple Store / Authorised Reseller | Dell Kenya / authorised partner |
| Est. Price (USD) | $3,500 | $4,200 |
| Lead Time | 2 weeks | 3 weeks |
| CPU | Apple M4 Max (16-core: 12 performance + 4 efficiency) | Intel Core i9-14900HX (24-core, up to 5.8 GHz) or AMD Ryzen 9 7945HXX |
| RAM | 64GB Unified Memory (LPDDR5) | 128GB DDR5 ECC (4x 32GB) |
| GPU | Apple M4 Max 40-core GPU | NVIDIA RTX 5000 Ada Generation (16GB GDDR6 ECC) |
| Storage | 2TB SSD (Apple Silicon integrated) | 2TB NVMe PCIe Gen 4 SSD (Samsung 990 Pro or equivalent) |
| Display | 16.2" Liquid Retina XDR, 3456x2234, 1000 nits XDR, P3 wide colour | 17.3" UHD+ (3840x2160) IPS, 100% DCI-P3, factory-calibrated |
| Ports | 3x Thunderbolt 5, HDMI 2.1, SDXC card slot, MagSafe 3, 3.5mm | 2x Thunderbolt 4, 2x USB-C 3.2, HDMI 2.1, SD card, RJ-45 2.5GbE, 3.5mm |
| Networking | Wi-Fi 6E (802.11ax), Bluetooth 5.3 | Wi-Fi 6E, Bluetooth 5.3, 2.5GbE RJ-45 |
| OS | macOS 15 Sequoia + Parallels Desktop (Windows 11 VM) | Windows 11 Pro + Ubuntu 24.04 LTS (dual boot) |
| Warranty | 3-year AppleCare+ Enterprise | 3-year Dell ProSupport Plus (next-business-day onsite) |

# 1.2 Backend / API Developer (x2)

Database-heavy development, API integration with government systems, queue/worker management. Windows/Linux preferred for .NET and native Docker.

| Spec | Primary (Intel/AMD) | Alternative (Mac) |
| --- | --- | --- |
| Model | Dell Precision 7780 Workstation | Apple MacBook Pro 16" M4 Max |
| Supplier | Dell Kenya | Apple Store |
| Est. Price (USD) | $4,200 | $3,500 |
| Lead Time | 3 weeks | 2 weeks |
| CPU | Intel Core i9-14900HX (24-core, up to 5.8 GHz) | M4 Max 16-core |
| RAM | 128GB DDR5 ECC (4x 32GB) | 64GB Unified |
| GPU | NVIDIA RTX 5000 Ada 16GB | 40-core GPU |
| Storage | 2TB NVMe PCIe Gen 4 SSD | 2TB SSD |
| Display | 17.3" UHD+ IPS, 100% DCI-P3 | 16.2" Liquid Retina XDR |
| OS | Windows 11 Pro + Ubuntu 24.04 LTS dual boot | macOS + Parallels Windows VM |
| Warranty | 3-year Dell ProSupport Plus | 3-year AppleCare+ Enterprise |

# 1.3 Frontend / Mobile Developer (x2)

React/Next.js frontend and React Native mobile. Mac preferred for Xcode/iOS builds.

| Spec | Primary (Mac) | Alternative (Intel/AMD) |
| --- | --- | --- |
| Model | Apple MacBook Pro 16" M4 Max | Dell Precision 7780 |
| Price | $3,500 | $4,200 |
| CPU | M4 Max 16-core | i9-14900HX |
| RAM | 64GB Unified | 128GB DDR5 |
| GPU | 40-core GPU | RTX 5000 Ada 16GB |
| Storage | 2TB SSD | 2TB NVMe |
| Display | 16.2" Liquid Retina XDR | 17.3" UHD+ |
| Key Reason | Native iOS/Xcode builds, better frontend tooling ecosystem | Fallback if Mac unavailable |

# 1.4 Security Engineer (x2)

Pentesting, SIEM, vulnerability assessment. Dual-boot Linux/Windows required for security tooling.

| Spec | Primary | Alternative |
| --- | --- | --- |
| Model | Dell Precision 7780 | Lenovo ThinkPad P16 Gen 3 |
| Supplier | Dell Kenya | Lenovo Kenya |
| Price | $5,500 | $5,200 |
| Lead Time | 3 weeks | 3 weeks |
| CPU | Intel Core i9-14900HX | Intel Core i9-14900HX |
| RAM | 128GB DDR5 ECC | 128GB DDR5 ECC |
| GPU | NVIDIA RTX 5000 Ada 16GB | NVIDIA RTX 5000 Ada 16GB |
| Storage | 4TB NVMe (2x 2TB RAID 1, hardware-encrypted Opal 2.0) | 4TB NVMe (2x 2TB RAID 1) |
| Display | 17.3" UHD+ IPS matte, 100% sRGB | 16" 4K OLED, 100% DCI-P3 |
| Networking | 10GbE RJ-45 + Wi-Fi 6E + Bluetooth 5.3 | 2.5GbE + Wi-Fi 6E |
| Security Features | TPM 2.0, fingerprint, IR camera, chassis intrusion, Kensington lock | TPM 2.0, fingerprint, IR camera, dTPM, Kensington lock |
| OS | Windows 11 Pro + Ubuntu 24.04 LTS (dual boot) + Kali Linux VM | Windows 11 Pro + Ubuntu 24.04 LTS (dual boot) + Kali VM |
| VPN | Hardware VPN token (GovNet-compatible) | Hardware VPN token (GovNet-compatible) |
| Warranty | 3-year ProSupport Plus (4-hour onsite) | 3-year Premier Support (onsite) |

# 1.5 3D Artist (Mobile/Field) (x2)

Field-ready workstation for previewing 3D assets on location, light modelling, and asset review.

| Spec | Primary (Mac) | Alternative |
| --- | --- | --- |
| Model | Apple MacBook Pro 16" M4 Max | Dell Precision 7780 |
| Price | $5,500 | $5,500 |
| CPU | M4 Max 16-core | i9-14900HX |
| RAM | 128GB Unified | 128GB DDR5 |
| GPU | 40-core GPU | RTX 5000 Ada 16GB |
| Storage | 4TB SSD | 4TB NVMe |
| Display | 16.2" mini-LED, 1600 nits peak HDR, P3 wide colour | 17.3" UHD+ IPS, 100% DCI-P3 |
| Rationale | Mac preferred for creative apps ecosystem (Maya, Blender, Adobe). Dell as backup. |  |

# Workstation Order Summary

| Role | Qty | Primary | Alternative | Unit Price | Total (USD) |
| --- | --- | --- | --- | --- | --- |
| Lead Full-Stack Dev | 2 | MacBook Pro 16" M4 Max 64GB | Dell Precision 7780 | $3,500 | $7,000 |
| Backend/API Dev | 2 | Dell Precision 7780 | MacBook Pro 16" M4 Max | $4,200 | $8,400 |
| Frontend/Mobile Dev | 2 | MacBook Pro 16" M4 Max 64GB | Dell Precision 7780 | $3,500 | $7,000 |
| Security Engineer | 2 | Dell Precision 7780 128GB+4TB | Lenovo ThinkPad P16 Gen 3 | $5,500 | $11,000 |
| 3D Artist (Mobile) | 2 | MacBook Pro 16" M4 Max 128GB | Dell Precision 7780 | $5,500 | $11,000 |
| TOTAL WORKSTATIONS | 10 |  |  |  | $44,400 |

# 2. Software Licenses — Detailed Orders

All software licenses are annual subscriptions unless noted as perpetual. Order immediately as they are delivered digitally.

| Qty | Software | License Type | Annual Cost (USD) | Order URL / Vendor | Notes |
| --- | --- | --- | --- | --- | --- |
| 8 | JetBrains All Products Pack (incl. DataGrip, PyCharm, IntelliJ, Rider, WebStorm) | Per-seat annual subscription | $749/seat = $5,992 | jetbrains.com (education discount available) | Every developer needs this. Covers all languages used. |
| 8 | GitHub Enterprise | Per-user monthly billing | $21/user/mo = $2,016/yr | github.com/enterprise | Source control, CI/CD, project management, code review. |
| 8 | Jira / Linear (project management) | Per-user monthly | $15/user/mo = $1,440/yr | atlassian.com / linear.app | Sprint planning, issue tracking, product backlog. |
| 4 | Adobe Creative Cloud All Apps | Per-seat annual | $996/seat = $3,984 | adobe.com/education | Photoshop, Illustrator, Premiere Pro, After Effects, etc. |
| 2 | DaVinci Resolve Studio | Perpetual (one-time) | $295 x 2 = $590 | blackmagicdesign.com | Colour grading for 4D cinematic content. One-time purchase. |
| 10 | CrowdStrike Falcon (endpoint protection) | Per-endpoint annual | $250/endpoint = $2,500 | crowdstrike.com | Antivirus, EDR, threat hunting on every workstation. |
| 1 | Wazuh SIEM | Open-source (free) | $0 (free) | wazuh.com | Security monitoring and log analysis. Use free community edition. |
| TOTAL SOFTWARE (1st year) |  |  | $16,522 |  |  |

# 3. Storage & Infrastructure — Detailed

This is your entire media asset backbone. Every 4K video, 360° tour, 3D model, and project file lives here.

# 3.1 Primary NAS

| Spec | Detail |
| --- | --- |
| Model | Synology RS3624RPxs (rackmount, 12-bay) |
| Drives | 12x Seagate Exos X24 24TB 7200rpm SAS (enterprise-grade, 2.5M hr MTBF) |
| RAID | RAID 6 (dual parity) = 192TB usable. Hot spare included. |
| Cache | 2x Samsung 990 Pro 2TB NVMe SSD (read + write cache) |
| Networking | Dual 10GbE RJ-45 + dual 25GbE SFP28 (use SFP28 for render farm connection) |
| RAM | 64GB DDR5 ECC (expandable to 256GB) |
| Redundancy | Dual redundant power supplies (hot-swappable) |
| UPS | APC Smart-UPS 3000VA (provides 30 min runtime for graceful shutdown) |
| Estimated Total | $12,000 (NAS) + $6,000 (drives) + $1,200 (NVMe cache) + $1,500 (UPS) = $20,700 |
| Supplier | Synology authorised Kenya partner / CDW |
| Lead Time | 2-3 weeks |

# 3.2 Backup NAS

| Spec | Detail |
| --- | --- |
| Model | Synology RXD1219sas (expansion chassis, 12-bay) |
| Drives | 12x Seagate Exos X24 24TB (same as primary for swap compatibility) |
| RAID | RAID 6 = 192TB usable |
| Connection | Connect to primary NAS via InfiniBand or 25GbE for fast backup |
| Rotation | Full backup nightly. Complete backup taken off-site weekly (rotated between two locations). |
| Estimated Total | $8,000 (chassis) + $6,000 (drives) = $14,000 |

# 3.3 Field Backup Servers (x2)

Portable SSD storage for field teams. Each camera operator offloads media cards to this at end of every capture day.

| Spec | Detail |
| --- | --- |
| Model | QNAP TVS-h874-i9 (tower, 8-bay, Intel Core i9-13900) |
| Drives | 4x Samsung 870 EVO 8TB SSD (RAID 5 = 24TB usable per unit) |
| Why SSD | No spinning disks = shock-proof for field transport. Silent. Low power. |
| Portability | Backpack-sized. Crated Pelican case for air travel. |
| Connectivity | 2x 2.5GbE RJ-45 + 2x USB-C 3.2 Gen2 + SD card slot |
| Offload Workflow | End of day: CFast/SD → Field Server (verified copy) → overnight sync to Primary NAS when connected |
| Estimated Total | $3,500 x 2 = $7,000 |

# Storage Order Summary

| Item | Qty | Unit Price | Total (USD) | Supplier |
| --- | --- | --- | --- | --- |
| Synology RS3624RPxs NAS | 1 | $12,000 | $12,000 | Synology Kenya / CDW |
| Seagate Exos X24 24TB (for NAS) | 24 | $500 | $12,000 | Seagate authorised partner |
| Samsung 990 Pro 2TB NVMe (cache) | 2 | $200 | $400 | Samsung / online |
| APC Smart-UPS 3000VA | 1 | $1,500 | $1,500 | APC Kenya distributor |
| Synology RXD1219sas expansion | 1 | $8,000 | $8,000 | Synology Kenya |
| QNAP TVS-h874-i9 + 4x8TB SSD | 2 | $3,500 | $7,000 | QNAP authorised partner |
| TOTAL STORAGE |  |  | $40,900 |  |

# 4. Audio Equipment — Detailed

Complete field audio capture kit for the content production team.

| Qty | Item | Model | Price (USD) | Supplier | Notes |
| --- | --- | --- | --- | --- | --- |
| 2 | Ambisonic Microphone | Sennheiser AMBEO VR Mic | $1,700 | Sennheiser Kenya / B&H | First-order ambisonic, 4 matched capsules, binaural monitoring. For Tier C spatial audio capture. |
| 2 | Field Recorder | Sound Devices MixPre-10 II | $1,500 | Sound Devices distributor / B&H | 10 inputs, 32-bit float (impossible to clip), timecode I/O, dual SD. The industry standard for field production. |
| 1 | Binaural Microphone | 3Dio Free Space Pro II + Sennheiser KE-213 | $900 | 3Dio direct / B&H | Human-ear form factor. Captures audio as human ears hear it. Essential for mobile VR/360° binaural content. |
| 2 | Boom Microphone | Sennheiser MKH 416 | $1,100 | Sennheiser Kenya / B&H | Short shotgun, RF condenser. Industry-standard location dialogue mic. Excellent off-axis rejection for noisy field environments. |
| 2 | Wireless Lavalier Kit | DJI Mic 2 (2TX + 1RX + charging case per kit) | $350 | DJI Kenya / online | 250m range, internal recording backup (14-bit, 48kHz). Perfect for interviews with exhibitors and county officials. |
| 2 | Boom Pole | K-Tek Aura Plus (carbon fibre, 3-6m extendable) | $500 | K-Tek distributor / B&H | Internal cable routing, internal dampening. Lightweight for all-day field use. |
| 1 | Wind Protection Kit | RyCote Blimp (full kit + furry windscreen) | $400 | RyCote distributor | Full wind isolation for MKH 416 boom. Essential for outdoor locations (highlands, open plains, coast). |
| Accessories |  |  |  |  |  |
| 1 | XLR Cable Set | Canare Star Quad (4x 5m, 2x 10m, 2x 20m) | $300 | Local audio supplier | Balanced, shielded. Various lengths for different field setups. |
| 1 | Boom Stand | K&M 21470 (heavy-duty telescopic, 1.5-3.5m) | $200 | K&M distributor | For stationary interview setups. |
| 1 | Headphones | Sony MDR-7506 (standard) + Beyerdynamic DT 1990 Pro (critical listening) | $650 | Sony / Beyerdynamic | MDR-7506 for field monitoring. DT 1990 Pro for studio-level editing and spatial audio QC. |
| 1 | Memory Cards | Kingston Canvas Go! Plus 256GB SDXC (6x) | $300 | Online / local | High-speed UHS-II for 32-bit float multi-track recording. |
| 1 | Battery Kit | NP-F970 batteries (4x) + dual charger | $200 | Online / local | All-day field recording on single charge set. |
| 1 | Pelican Case | Pelican 1510 (carry-on size) with custom foam | $200 | Pelican Kenya | Safe transport for all audio gear. |
| TOTAL AUDIO KIT |  |  | $8,800 |  |  |

# 5. Staff — Detailed Hiring Plan

20 people to hire in Month 1. Job descriptions summarised. Advertise in Month 0 to have candidates ready.

# 5.1 Engineering Roles

| Role | Qty | Monthly (KES) | Annual (KES) | Minimum Qualifications | Interview Focus |
| --- | --- | --- | --- | --- | --- |
| Full-Stack Laravel/PHP Engineer | 4 | 250,000 | 3,000,000 | BSc Computer Science or equivalent. 3+ years Laravel, MySQL, REST APIs. Experience with Redis, queues, and payment integrations. | Live coding: build a Laravel API endpoint with validation, DB query, and JSON response. Ask about scaling MySQL queries. |
| Python/ML Engineer | 2 | 300,000 | 3,600,000 | BSc/MSc in CS, ML, or Data Science. 3+ years Python. Experience with PyTorch or scikit-learn. NLP/embedding experience strongly preferred. | Present a past ML project. Test: explain how a recommendation system works and how you'd handle cold-start. |
| Frontend Developer (React/Next.js) | 2 | 220,000 | 2,640,000 | BSc CS or equivalent. 3+ years React, TypeScript. Experience with Next.js, Tailwind or Bootstrap. Knowledge of responsive design and API integration. | Portfolio review. Live: build a responsive dashboard component that fetches and displays API data. |
| Mobile Developer (Unity/C#) | 2 | 280,000 | 3,360,000 | BSc CS or Game Dev. 2+ years Unity, C#. Experience building and shipping iOS and Android apps. 3D rendering optimisation knowledge essential. | Portfolio of shipped apps. Test: explain draw calls, LODs, and how you'd optimise a 3D scene for mobile. |
| Cybersecurity Engineer | 2 | 350,000 | 4,200,000 | BSc CS/Cybersec or equivalent. 3+ years security engineering. Certified: OSCP, CEH, or CISSP (at least one). Experience with Burp Suite, Wazuh, and pentesting methodologies. | Practical: demonstrate a pentesting methodology. Walk through how you'd secure a Laravel API. |
| Database Administrator | 1 | 250,000 | 3,000,000 | BSc CS or equivalent. 5+ years MySQL/MariaDB administration. Expert in query optimisation, replication, backup/DR. Percona Toolkit experience. | Practical: given a slow query with EXPLAIN output, diagnose and fix. Ask about migration strategies for zero-downtime. |
| DevOps Engineer | 1 | 280,000 | 3,360,000 | BSc CS or equivalent. 3+ years Linux (Ubuntu), Nginx, Docker, CI/CD. Experience with GitHub Actions, monitoring (Prometheus/Grafana), and cloud/VPS provisioning. | Practical: design a CI/CD pipeline for a Laravel app with automated testing, staging, and zero-downtime production deployment. |
| Technical Lead / Architect | 1 | 450,000 | 5,400,000 | BSc/MSc CS. 7+ years full-stack development. 3+ years technical leadership. Proven architecture experience with Laravel, Python, and high-scale systems. Must have built and shipped a complex platform. | System design session: design a system handling 1M+ daily API requests. Review their past architecture decisions and trade-offs. |
| Product Manager | 1 | 300,000 | 3,600,000 | BSc or MBA. 5+ years product management. Experience with B2B/B2G platforms. Knowledge of agile/scrum. County government experience is a strong plus. | Case study: prioritise 20 features with competing stakeholder interests. Ask about experience managing government relationships. |
| QA Engineer | 1 | 200,000 | 2,400,000 | BSc CS or equivalent. 3+ years QA engineering. Experience with PHPUnit, Laravel Dusk or Selenium, and k6 or JMeter. Must be able to write automated test suites. | Practical: write unit + integration tests for a given Laravel endpoint. Design a test plan for a payment flow. |

# 5.2 Operations Roles

| Role | Qty | Monthly (KES) | Annual (KES) | Minimum Qualifications | Interview Focus |
| --- | --- | --- | --- | --- | --- |
| Platform Administrator | 2 | 150,000 | 1,800,000 | Diploma or degree. 1+ year in content moderation, user support, or vendor verification. Comfortable with admin panels and spreadsheets. Good communication skills. | Scenario: how do you handle a vendor who uploaded prohibited content? Walk through the moderation process. |
| Content Manager / Coordinator | 1 | 180,000 | 2,160,000 | Degree in project management, communications, or related field. 3+ years production coordination. Experience scheduling field crews, managing permits, or county government liaison is a strong plus. | Case study: plan a 5-county capture trip with 3 field teams, including permitting, crew scheduling, and equipment logistics. |

# Staff Cost Summary — Month 1

| Category | Headcount | Monthly Cost (KES) | Annual Cost (KES) |
| --- | --- | --- | --- |
| Engineering (Tech Lead, Full-Stack, ML, Frontend, Mobile, Security, DBA, DevOps, QA) | 16 | KES 4,230,000 | KES 50,760,000 |
| Operations (Platform Admin, Content Coordinator) | 3 | KES 480,000 | KES 5,760,000 |
| Product (Product Manager) | 1 | KES 300,000 | KES 3,600,000 |
| TOTAL | 20 | KES 4,960,000 | KES 59,520,000 |

# 6. Office & Studio Setup (Month 1)

Workstations need a physical space. Minimum setup for the Phase 0 team.

| Item | Qty | Specification | Est. Cost (KES) |
| --- | --- | --- | --- |
| Ergonomic Desk | 10 | Electric height-adjustable (standing/sitting), 150x75cm | KES 25,000 each = 250,000 |
| Ergonomic Chair | 10 | Herman Miller Aeron or equivalent | KES 80,000 each = 800,000 |
| External Monitor | 10 | Dell U3224KB 32" 6K or Apple Studio Display 27" 5K | KES 150,000 each = 1,500,000 |
| Keyboard + Mouse | 10 | Logitech MX Master 3S + Keychron Q1 mechanical | KES 25,000 each = 250,000 |
| Meeting Room Display | 1 | Samsung 75" 4K QLED + Google Meet hardware | KES 300,000 |
| High-Speed Internet | 1 | Dedicated fibre: 500Mbps symmetric (Safaricom or Zuku Business) | KES 50,000/month |
| Office Space Rent | 1 | Nairobi Westlands/Upper Hill, approx 200sqm for 20 people | KES 400,000/month |
| Server Rack | 1 | 42U open-frame rack with cooling | KES 150,000 |
| Printer / Scanner | 1 | Multifunction laser (Kyocera or HP) | KES 80,000 |
| Stationery & Consumables | 1 | Whiteboards, markers, cabling, power strips, lockers | KES 200,000 |
| TOTAL SETUP |  |  | KES 3,980,000 (one-time) |
| TOTAL MONTHLY OVERHEAD |  |  | KES 450,000 (fibre + rent + power) |

# 7. Master Order List — Everything to Buy in Month 1

Print this page. Hand it to the procurement officer.

| # | Item | Qty | Est. USD | Est. KES | Supplier | When to Order |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Apple MacBook Pro 16" M4 Max 64GB/2TB | 2 | $7,000 | KES 910,000 | Apple Store / iStore Kenya | Day 1 |
| 2 | Dell Precision 7780 i9/128GB/RTX5000/2TB | 2 | $8,400 | KES 1,092,000 | Dell Kenya | Day 1 |
| 3 | Apple MacBook Pro 16" M4 Max 64GB/2TB (frontend) | 2 | $7,000 | KES 910,000 | Apple Store | Day 1 |
| 4 | Dell Precision 7780 i9/128GB/RTX5000/4TB RAID + Lenovo ThinkPad P16 | 2 | $11,000 | KES 1,430,000 | Dell + Lenovo Kenya | Day 1 |
| 5 | Apple MacBook Pro 16" M4 Max 128GB/4TB | 2 | $11,000 | KES 1,430,000 | Apple Store | Day 1 |
| 6 | JetBrains All Products Pack (8 licenses) | 8 | $5,992 | KES 779,000 | jetbrains.com | Day 1 (digital) |
| 7 | GitHub Enterprise (8 users) | 8 | $2,016 | KES 262,000 | github.com | Day 1 (digital) |
| 8 | Jira / Linear (8 users) | 8 | $1,440 | KES 187,000 | atlassian.com | Day 1 (digital) |
| 9 | Adobe Creative Cloud All Apps (4 licenses) | 4 | $3,984 | KES 518,000 | adobe.com | Day 1 (digital) |
| 10 | DaVinci Resolve Studio (2 perpetual) | 2 | $590 | KES 77,000 | blackmagicdesign.com | Day 1 (digital) |
| 11 | CrowdStrike Falcon (10 endpoints) | 10 | $2,500 | KES 325,000 | crowdstrike.com | Day 1 (digital) |
| 12 | Synology RS3624RPxs + 12x 24TB drives + NVMe cache | 1 | $18,600 | KES 2,418,000 | Synology Kenya / CDW | Day 1 |
| 13 | Synology RXD1219sas + 12x 24TB drives | 1 | $14,000 | KES 1,820,000 | Synology Kenya | Day 1 |
| 14 | QNAP TVS-h874-i9 + 4x 8TB SSD (x2) | 2 | $7,000 | KES 910,000 | QNAP partner | Day 1 |
| 15 | APC Smart-UPS 3000VA | 1 | $1,500 | KES 195,000 | APC Kenya | Day 1 |
| 16 | Audio field kit (all items per Section 4) | 1 | $8,800 | KES 1,144,000 | B&H / local suppliers | Day 1 |
| 17 | Office furniture + monitors + setup | 1 | $30,600 | KES 3,980,000 | Local furniture + Dell monitors | Week 1 |
| TOTAL |  |  | $121,022 | KES 15,733,000 |  |  |

Notes: USD prices are approximate. KES conversion at 130. Obtain current quotes. Add 15% for shipping, taxes, and import duties.

# 8. Team Leader — Week 1 Action Checklist

| Day | Task | Owner | Priority |
| --- | --- | --- | --- |
| Day 1 | Place all workstation orders with Apple, Dell, Lenovo | Procurement | Critical |
| Day 1 | Purchase all software licenses online | CTO / Tech Lead | Critical |
| Day 1 | Place NAS and storage orders with Synology/QNAP Kenya partner | Procurement | Critical |
| Day 1 | Place audio equipment order | Content Manager | High |
| Day 1 | Start recruitment process: publish all 8 job advertisements | HR / Team Leader | Critical |
| Day 2 | Confirm office space lease (200sqm, Westlands/Upper Hill) | Team Leader | High |
| Day 2 | Order office furniture, monitors, and IT consumables | Procurement | High |
| Day 2 | Apply for dedicated fibre internet connection | Team Leader | Medium |
| Day 2 | Register domain names and set up DNS | Tech Lead | Medium |
| Day 3 | Set up GitHub organisation, Jira/Linear workspace | Tech Lead | High |
| Day 3 | Set up CrowdStrike endpoint management console | Security Engineer | High |
| Day 3 | Begin candidate shortlisting for engineering roles | HR | Critical |
| Day 3 | Contact Synology/QNAP for on-site installation support | IT / DevOps | Medium |
| Day 4 | Draft Data Protection Act registration with Data Commissioner | Security Engineer / Legal | High |
| Day 4 | Contact NIS office to initiate security coordination | Security Engineer | High |
| Day 4 | Begin onboarding checklist for new hires (docs, policies, equipment) | HR | Medium |
| Day 5 | Review all orders: confirm delivery dates, escalate delays | Team Leader | High |
| Day 5 | First team stand-up meeting (remote or space permitting) | Tech Lead | Medium |
| Week 2+ | Receive workstations (Mac 2-week lead time). Begin setup and environment configuration. | DevOps + All | Critical |
| Week 3+ | Receive Dell workstations (3-week lead time). Continue setup. | DevOps | Critical |
| Week 3-4 | NAS arrives. Setup storage, create share structure, test backup. | DevOps + DBA | High |
| Week 3-4 | Audio kit arrives. Test, inventory, train camera team. | Content Manager | High |
| Week 4 | All 20 staff onboarded. Full team operating. | Team Leader | Critical |
| Week 4 | Phase 0 complete. Ready to order Phase 1 equipment. | Team Leader | Gateway |

# 9. Phase 0 Budget — One Page Summary

| Category | USD | KES (at 130) | Notes |
| --- | --- | --- | --- |
| Workstations (10 units) | $44,400 | KES 5,772,000 | MacBook Pro + Dell Precision + Lenovo |
| Software Licenses (Year 1) | $16,522 | KES 2,148,000 | JetBrains, GitHub, Jira, Adobe, DaVinci, CrowdStrike |
| Storage Infrastructure | $40,900 | KES 5,317,000 | Primary NAS, backup NAS, 2x field servers, UPS |
| Audio Field Kit | $8,800 | KES 1,144,000 | AMBEO, MixPre-10, MKH 416, DJI Mic 2, etc. |
| Office Setup (One-time) | $30,600 | KES 3,978,000 | Desks, chairs, monitors, meeting room, server rack |
| Staff (Month 1) | $38,154 | KES 4,960,000 | 20 people x average KES 248,000/month |
| Contingency (15%) | $26,000 | KES 3,380,000 | Shipping, taxes, duties, price changes |
| TOTAL PHASE 0 | $205,376 | KES 26,699,000 |  |

For approval: Total Phase 0 investment is approximately USD 205,000 (KES 27 million). This covers everything needed for the engineering team to begin building the platform. No Phase 1 spend is required until Phase 0 items are delivered and staff are onboarded.